## Slide 1: The Recorded Home Oximetry (RHO) Program Monthly Investigator Meeting
July 1, 2021

## Slide 2: Site Selection for Implementation Waves
Wave 1
Dartmouth Hitchcock Medical Center
Boston Children’s Hospital
Massachusetts General Hospital
Maria Fereri Children’s Hospital
University of Maryland
Vanderbilt
Wave 2
Arkansas Children’s Hospital
Children’s Hospital of Philadelphia
Cincinnati Children’s Hospital
National Jewish Health
Nationwide Children’s Hospital
Peyton Manning Children’s Hospital
University of California, San Diego
University of Kentucky

## Slide 3: RHO Program Implementation Timeline: Wave 1 Sites
February 2021
Baseline data collection begins
March 2021
Initiate site training
Initiate monthly phone calls
May 2021
June-August 2021
February 2022
August 2022
Complete site training
Reach 33% of eligible families
Reach 66% of eligible families
February 2023
Reach 100% of eligible families
Initiate 18-month implementation
Begin providing monthly feedback reports

## Slide 4: RHO Program Implementation Timeline: Wave 2 Sites
March 2021
Baseline data collection begins
May 2021
Initiate site training
August 2021
December 2021-February 2022
August 2022
February 2023
Complete site training
Reach 33% of eligible families
Reach 66% of eligible families
August 2023
Reach 100% of eligible families
Initiate 18-month implementation
Begin providing monthly feedback reports

## Slide 5: Site Training Planning
Wave 1 Site Visits Completed
2/8 Wave 2 Visits Completed
4/8 Wave 2 Site Visits Scheduled
Masimo coordinating times to meet with sites identified home care companies
  Heather has also been conducting information sessions with each site’s designated home care companies

## Slide 6: Updates on IRB Approval
Due to delay in SMART IRB submissions of wave 2 sites please start the process with your IRB’s now
If your IRB is requiring written informed consent- do not cede approval to UMMS
If referring hospitals are to provide VON data separate IRB will be executed- Heather working on protocol
pSite forms will be disseminated once individual site IRB has ceded approval

## Slide 7: Questions or concerns regarding IRB approval?
Site specific problems we can help with?

## Slide 8: Home Care Companies Providing Masimo RAD 97s
Chart: Available Home Care Companies Providing RAD 97s
| Dartmouth-Hitchcock Medical Center | Vanderbilt University Medical Center | National Jewish Health for Kids, Denver | Children's Hospital of Philadelphia | Massachusetts General Hospital | Boston Children's Hospital | Arkansas Children's Hospital | Nationwide Children's Hospital | University of Maryland Baltimore | University of California, San Diego | Maria Fareri Children's Hospital | Cincinnati Children's Hospital | St. Vincent Neightborhood Hospital
RAD 97 Available | 3 | 2 | 1 | 2 | 2 | 2 | 1 | 3 | 3 | 2 | 1 | 1 | 0
RAD 97 Unavailable | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 5 | 2
Unknown | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 4 | 6 | 3 | 3 | 0 | 2
57% of sites have met the target amount of home cares!

## Slide 9: Site Progress on Implementation Start-Up
Site Name | Contract Executed | cIRB Approval | Local IRB Approval | Regulatory Documents | pSite Communication Plan Agreement | Site Training Completed | Site Implementation Date | First Enrollment Date | Downloading Schedule
Boston Children's Hospital | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 6/1/2021 |  | M/T
Dartmouth-Hitchcock | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 6/1/2021 |  | T/F
Maria Fareri Children's | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | 6/1/2021 |  | M/T
Massachusetts General Hospital | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 6/1/2021 |  | M/T
University of Maryland | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 6/1/2021 |  | M/T
Vanderbilit | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | 6/1/2021 |  | T/F
Arkansas Children's Hospital | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD
Children's Hospital of Phil. | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD
Cincinatti Children's Hospital | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD
National Jewish Health | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD
Nationwide Children's Hospital | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD
Peyton Manning Children's Hospital | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD
U. of California, San Diego | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD
U. of Kentucky Children's Hospital | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD

## Slide 10: REDCap User Access Groups
Please notify Lindsey and Heather once you have been granted UMass REDCap approval to be added to your site’s data access group

## Slide 11: Timing of Data Collection
Pre-Implementation Data
Goal to send VON and additional outpatient variable data within 3 months of implementation go-live
Implementation Data
Screening and Eligibility: Prior to NICU discharge
Demographics: At or around time of NICU discharge
Home Oximetry Data Form: In real-time by your site’s DCC
Adverse Events: Upon learning of adverse event
Implementation Discharge: Upon HOT discontinuation
Emailed to UMass RHO Study Team
Uploaded into RHO REDCap through DAG

## Slide 12: Timing of Data Collection
Pre-Implementation Data
Goal to send VON and additional outpatient variable data within 3 months of implementation go-live
Implementation Data
Screening and Eligibility: Prior to NICU discharge
Demographics: At or around time of NICU discharge
Home Oximetry Data Form: In real-time by your site’s DCC
Adverse Events: Upon learning of adverse event
Implementation Discharge: Upon HOT discontinuation
Emailed to UMass RHO Study Team
Uploaded into RHO REDCap through DAG
At 6-months post-discontinuation of HOT
Notes: We will be supplying the timeline and dates forms are to be collected in monthly site reports
Adverse events are to be followed for 6-months post discontinuation of HOT

## Slide 13: Weaning Increments and Decrements of the RHO Program
Oxygen flow rates will be weaned in 50% decrements (or increased 50% increments)
What are your sites normal titrations?
Sprints?
Lowest comfortable continuous oxygen flow rate?

## Slide 14: Closing Thoughts
Questions and Comments