## Slide 1: The Recorded Home Oximetry (RHO) Program Monthly Investigator Meeting
May 5, 2022

## Slide 2: RHO Program Implementation Timeline
Feb - Mar 2021
Baseline data collection begins
Mar - May 2021
Initiate site training
Initiate monthly phone calls
May - Aug 2021
Jun 2021 - Feb 2022
Feb - Aug 2022
Aug 2022 - Feb 2023
Complete site training
Reach 33% of eligible families
Reach 66% of eligible families
Feb - Aug 2023
Reach 100% of eligible families
Initiate 18-month implementation
Begin providing monthly feedback reports

## Slide 3
Chart: Site Start Up Progress
| Vanderbilt | Maryland | Kentucky | San Diego | Peyton Manning | Nationwide | Colorado | MGH | New York | Dartmouth | Cincinnati | CHOP | BCH | Arkansas
Executed Contract | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
IRB Approval | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
Equipment Available | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
 | - Enrolling
 | - Activated but not enrolling
 | - Patient identified, not yet enrolled

## Slide 4: RHO Implementation Trial Consort Diagram
Average HOT Duration:
71 ± 56

## Slide 5
Goal
Chart: Recorded Home Oximetry Program Implementation Trial Enrollment (July 2021 to Present)
| Jul-21 | Aug-21 | Sep-21 | Oct-21 | Nov-21 | Dec-21 | Jan-22 | Feb-22 | Mar-22 | Apr-22 | May-22
Participants Enrolled | 3 | 3 | 1 | 5 | 5 | 1 | 8 | 3 | 8 | 3 | 1
UCL | 9.5191 | 9.5191 | 9.5191 | 9.5191 | 9.5191 | 9.5191 | 9.5191 | 9.5191 | 9.5191 | 9.5191 | 9.5191
+2 Sigma | 7.5885 | 7.5885 | 7.5885 | 7.5885 | 7.5885 | 7.5885 | 7.5885 | 7.5885 | 7.5885 | 7.5885 | 7.5885
+1 Sigma | 5.6579 | 5.6579 | 5.6579 | 5.6579 | 5.6579 | 5.6579 | 5.6579 | 5.6579 | 5.6579 | 5.6579 | 5.6579
Average | 3.7273 | 3.7273 | 3.7273 | 3.7273 | 3.7273 | 3.7273 | 3.7273 | 3.7273 | 3.7273 | 3.7273 | 3.7273
-1 Sigma | 1.7967 | 1.7967 | 1.7967 | 1.7967 | 1.7967 | 1.7967 | 1.7967 | 1.7967 | 1.7967 | 1.7967 | 1.7967
-2 Sigma | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LCL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enrollment Goal Per Month | 3.8 | 4.3 | 4.3 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9

## Slide 6: Projected vs. Actual Enrollment Into the RHO Program
Site Name | Site IRB Approved | Estimate per Year | Estimate per Month | Current per Month
WAVE 1 |  |  |  | 
Boston Children's Hospital | 10/4/2021 | 40 | 3.3 | 0.8
Dartmouth-Hitchcock | 10/4/2021 | 20 | 1.7 | 0.8
Maria Fareri Children's | 7/10/2021 | 14 | 1.2 | 0.4
Massachusetts General Hospital | 10/4/2021 | 13 | 1.1 | 0.6
University of Maryland | 10/4/2021 | 20 | 1.7 | 0.7
Vanderbilt | 7/21/2021 | 70 | 5.8 | 0.1
WAVE 2 |  |  |  | 
Arkansas Children's Hospital | 1/28/2022 | 48 | 4.0 | 0.6
Children's Hospital of Phil. | 10/20/2021 | 50 | 4.2 | 0.0
Cincinnati Children's Hospital | 4/15/2022 | 50 | 4.2 | 
National Jewish Health | 10/4/2021 | 250 | 20.8 | 0.0
Nationwide Children's Hospital | 10/4/2021 | Not Provided | Not Provided | 0.7
Peyton Manning Children's Hospital |  | 25 | 2.1 | 
U. of California, San Diego | 10/4/2021 | 65 | 5.4 | 0.8
U. of Kentucky Children's Hospital |  | 50 | 4.2 | 

## Slide 7: Barriers to Enrollment
Screening Logs:
  Please ensure your site is screening ALL potentially eligible infants discharged home on respiratory support despite their participation status in the RHO program
  Completion of the screening form in REDCap is essential in the accuracy of the overall denominator and ensuring all eligible infants are captured across all sites
  Proper completion of the screening form would further aid in providing an accurate reach of the RHO program- a primary outcome of the implementation trial

## Slide 8: Barriers to Enrollment Continued
Demographic Forms:
  Please ensure your site is filling-out demographic forms for ALL eligible infants discharged on supplemental oxygen despite their participation status in the RHO program
  Completion of the demographics form is essential for the individualized monthly site reports, which are sent out to all active sites on the 15th of each month
  The following forms should be completed in the project’s REDCap for infants who are eligible but aren’t followed by the program but opt-in to data collection
    1. Screening and Eligibility form
    2. Demographics form
    3. Implementation Discharge form (essential to obtain HOT duration on ALL eligible infants for future analysis)
    4. Adverse Events form

## Slide 9: Baseline Data
As a reminder, all sites are required to submit their VON and Additional baseline data
Templates and instructions on how to extract and format the data can be found on the RHO website
2/14 sites have submitted both sets of baseline data
Please reach out to Heather with any questions

## Slide 10: Clarification on SAE Definition
Modification accepted to clarify definition and reporting of SAE’s
For this study, events related to underlying prematurity and in the opinion of the site investigator not outside the normal course for a preterm infant diagnosed with BPD on HOT and associated equipment
SAE’s are to be reported promptly to Heather and reported to the IRB and DSMB within 72-hours of the occurrence
The first DSMB meeting will occur this month

## Slide 11: Family Engagement Survey
  The Family Engagement Pre and Post Implementation Survey Project has been submitted to the UMass IRB
  Once approved, we will send an email to all sites with all appropriate documents to submit to your IRB
  Please reach out to Heather with any questions

## Slide 12: Implementation Related Problems

## Slide 13
Chart: Recorded Home Oximetry Implementation Trial Related Barriers and Problems
| 44378 | 44409 | 44440 | 44470 | 44501 | 44531 | 44562 | 44593 | 44621 | 44652
Problem Count | 1 | 6 | 2 | 1 | 6 | 4 | 5 | 8 | 5 | 6
UCL | 10.6929 | 10.6929 | 10.6929 | 10.6929 | 10.6929 | 10.6929 | 10.6929 | 10.6929 | 10.6929 | 10.6929
+2 Sigma | 8.5952 | 8.5952 | 8.5952 | 8.5952 | 8.5952 | 8.5952 | 8.5952 | 8.5952 | 8.5952 | 8.5952
+1 Sigma | 6.4976 | 6.4976 | 6.4976 | 6.4976 | 6.4976 | 6.4976 | 6.4976 | 6.4976 | 6.4976 | 6.4976
Average | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4
-1 Sigma | 2.3024 | 2.3024 | 2.3024 | 2.3024 | 2.3024 | 2.3024 | 2.3024 | 2.3024 | 2.3024 | 2.3024
-2 Sigma | 0.20476 | 0.20476 | 0.20476 | 0.20476 | 0.20476 | 0.20476 | 0.20476 | 0.20476 | 0.20476 | 0.20476
LCL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 14: Deviation Types
Chart: 
| Technological barrier with SafetyNet connection (no data captured) | Wi-Fi connectivity issues (no data captured) | Patient not connected to oximeter (no data captured) | Damaged equipment: probes, cord etc. (no data captured) | Wrong device provided (no data captured) | Currently Admitted (no data captured) | No data captured, reason unknown | Provider did not follow guideline suggestion | Did not meet minimum time but change in flow rate occurred anyway | Data was not analyzed at set time | Parent felt uncomfortable changing flow rate | Parent titrated flow rates | Unable to get in contact with parents to provide recommendation
 | 45 | 26 | 15 | 23 | 6 | 4 | 51 | 52 | 2 | 0 | 19 | 9 | 11
Total Reports | Reports with Deviation(s)
854 | 309 (36%)

## Slide 15
Goal
Chart: Percent Compliance with the Recorded Home Oximetry Algorithm Across All Implementation Sites
| Jul. 2021 (n=15) | Aug. 2021 (n=51) | Sept. 2021 (n=65) | Oct. 2021 (n=63) | Nov. 2021 (n=75) | Dec. 2021 (n=91) | Jan. 2022 (n=93) | Feb. 2022 (n=121) | Mar. 2022 (n=137) | Apr. 2022 (n=127)
Percent Compliance | 0.66667 | 0.94118 | 0.92308 | 0.9 | 0.91 | 0.96703 | 0.95699 | 0.93388 | 0.87591 | 0.86614
UCL | 1.037 | 1.037 | 1.037 | 1.037 | 1.037 | 1.037 | 1.037 | 1.037 | 1.037 | 1.037
+2 Sigma | 0.98938 | 0.98938 | 0.98938 | 0.98938 | 0.98938 | 0.98938 | 0.98938 | 0.98938 | 0.98938 | 0.98938
+1 Sigma | 0.94173 | 0.94173 | 0.94173 | 0.94173 | 0.94173 | 0.94173 | 0.94173 | 0.94173 | 0.94173 | 0.94173
Average | 0.89409 | 0.89409 | 0.89409 | 0.89409 | 0.89409 | 0.89409 | 0.89409 | 0.89409 | 0.89409 | 0.89409
-1 Sigma | 0.84644 | 0.84644 | 0.84644 | 0.84644 | 0.84644 | 0.84644 | 0.84644 | 0.84644 | 0.84644 | 0.84644
-2 Sigma | 0.7988 | 0.7988 | 0.7988 | 0.7988 | 0.7988 | 0.7988 | 0.7988 | 0.7988 | 0.7988 | 0.7988
LCL | 0.75115 | 0.75115 | 0.75115 | 0.75115 | 0.75115 | 0.75115 | 0.75115 | 0.75115 | 0.75115 | 0.75115

## Slide 16: Reason’s Why Provider’s Are Not Following the RHO Algorithm’s Recommendation
36% of the time the RHO Algorithm’s Recommendation is not being followed by providers
21 infants (51%) have had at least one report with the recommendation not being followed
  16 infants (39%) had more than one report with the recommendation not being followed
49% of times the provider has felt comfortable maintaining when the recommendation was to “increase” (4% overall)
Need to re-classify “others”
Chart: Reason's For Providers Not Following the RHO Algorithm's Decision
| Growth Concerns | Recent or Current Illness | Feeding Intolerance | Increased WOB | Felt Comfortable Maintaining | Patient Not Seen Outpatient Yet | Data Thought to be Artifact | Other
 | 0 | 0 | 2 | 0 | 38 | 4 | 12 | 41

## Slide 17
Chart: How Physician Compliance with the RHO Algorithm Impacts Duration of HOT
| 90 | 86.666666669999998 | 84.61538462 | 100 | 100 | 91.666666669999998 | 100 | 97.222222220000006 | 100 | 100 | 90.7 | 90 | 100 | 77.8 | 96.6 | 87.5 | 87.5 | 100 | 100 | 100 | 100 | 74.2 | 79.400000000000006 | 100 | 94.4 | 100 | 100 | 94.285714290000001 | 80.952380950000006 | 80 | 90.47619048 | 100
 | 62 | 53 | 38 | 27 | 90 | 127 | 28 | 120 | 25 | 83 | 245 | 28 | 60 | 79 | 97 | 19 | 77 | 22 | 77 | 28 | 23 | 119 | 112 | 64 | 75 | 13 | 9 | 119 | 65 | 42 | 64 | 19

## Slide 18: Duration of Oxygen by Initial Flow Rate at Discharge

## Slide 19: Troubleshooting Guide
Distributed to active sites this week
Will be updated with new information as it becomes available

## Slide 20: RHO Program Website
All resources, including training documents, the RHO manual, and other templates can be found on the RHO website at www.umassmed.edu/rho-program
Navigate to “Member Login” and log in with the following credentials to access the documents
  Username: RHO
  Password: Oximetry14

## Slide 21: Closing Thoughts
Questions or Comments?
Are there any suggestions and/or feedback on the progress of the program that you would like to share with the team at this time?